## Sheet1
S.No | Defect ID | Defect Description | Reported Date | Priority: C - Critical, M - Medium , S -Small | Assigned To | Status | Target Date | Defect Summary
1 | DE-301 | Registration form error (eg. Missing field validation) | 2024-02-20 | C | Smith | In progress | 2024-03-15 | Waiting for report form Developer
2 | DE-302 | Switching theme error | 2024-02-21 | S | Sanjay | Completed | 2024-03-16 | Modified in theme provider
3 | DE-303 | Adding to cart error | 2024-02-22 | C | Vignesh | Completed | 2024-03-17 | Rectified data fetching from DB
4 | DE-304 | Web content is not dynamic | 2024-02-23 | S | Arun | In progress | 2024-03-18 | Waiting for assests from designer
What is DSR?
A defect report is a document that has concise details about what defects are identified, what action steps make the defects show up, and what are the expected results instead of the application showing error (defect) while taking particular step by step actions. Defect reports are usually created by the Quality Assurance team and also by the end-users (customers). Often customers detect more defects and report them to the support team of the software development since the majority of the customers curiously tries out every feature in the application